## Sheet1
| Begin Longitude | Begin Latitude | Project Street | From Street | To Street | End Longitude | End Latitude | Year | Est Start | Est End
Arterial Reconstruction
| -89.6127 | 40.7329 | University St | War Memorial Dr | Forrest Hill | -89.613 | 40.725 | 2016 | June 2016 | Nov 2016
| -89.6035 | 40.7055 | Sheridan Rd | Eleanor Pl | McClure Ave | -89.6032 | 40.7178 | 2016 | Aug 2016 | Aug 2017
| -89.6035 | 40.7063 | Sheridan Bridge | I-74 Bridge | Richmond Ave | -89.6035 | 40.7063 | 2016 | May 2016 | May 2017
| -89.604 | 40.6825 | Adams St | Pecan | Persimmon | -89.604 | 40.6825 | 2016 | June 2016 | Nov 2016
| -89.6316 | 40.762 | Northmoor Rd | University Ave | Allen Rd | -89.6131 | 40.7615 | 2017 | July 2017 | Nov 2019
| -89.6495 | 40.8127 | Radnor Rd/ Alta Lane Intersection | Intersection | 800' Each Length | -89.6495 | 40.8127 | 2017 | July 2017 | Dec 2017
| -89.6385 | 40.6713 | Folkers Ave | Fremont St | Latrobe St | -89.6385 | 40.6713 | 2017 | May 2017 | Oct 2017
| -89.5971 | 40.675 | Macarthur Bridge |  |  | -89.5971 | 40.675 | 2018 | Mar 2018 | June 2019
| -89.6229 | 40.6805 | Western Ave | Lincoln Ave | Adams St | -89.6229 | 40.6805 | 2019
| -89.6036 | 40.7118 | Sheridan Rd | Richmond Ave | Eleanor Pl | -89.6034 | 40.7082 | 2019
| -89.6296 | 40.7473 | Glen Ave | War Memorial Dr | University Ave | -89.6153 | 40.747 | 2020
| -89.5936 | 40.725 | Forrest Hill Ave | Knoxville Ave | Wisconsin Ave | -89.5936 | 40.725 | 2020
Pavement 2017
|  |  | Apple St | SW Washington St | SW Adams St |  |  | 2017 | August | August | SEALCOAT
|  |  | Blaine St | WASHINGTON | ALLEY |  |  |  | October | October | CRF
|  |  | N Arbor Dr | JAMES | BIG HOLLOW |  |  |  | October | October | CRF
|  |  | N Bestor St | W Columbian Ter | N end N of W Armstrong Ave |  |  |  | August | August | SEALCOAT
|  |  | N Brompton Ct | BROMPTON | EOP SOUTH |  |  |  | August | August | SLURRY SEAL
|  |  | N Chad Ct | N Talisman Terr | W Heidi Ct |  |  |  | August | August | SEALCOAT
|  |  | N Forrest Dr | SOUTH FOREST | OAKVIEW |  |  |  | August | August | SLURRY SEAL
|  |  | N Great Oak Rd | 1609 N Great Oak Rd | Cul-de-sace |  |  |  | August | August | SLURRY SEAL
|  |  | N Hunters Trce | ASPEN | FOX POINT |  |  |  | October | October | CRF
|  |  | N Indiana Ave | E Thrush Ave | E McClure Ave |  |  |  | August | August | SEALCOAT
|  |  | N Institute Pl | N Gale Ave | McClure |  |  |  | August | August | SEALCOAT
|  |  | N Isabell Ave | W Oakglen Dr | W Burnside Dr |  |  |  | August | August | SEALCOAT
|  |  | N Kane St | W Fourth St | W Aiken Ave |  |  |  | August | August | SEALCOAT
|  |  | N N State St | DR MARTIN LUTHER KING JR | EOP NORTH |  |  |  | October | October | CRF
|  |  | N New York Ave | E Pennsylvania Ave | E Nebraska Ave |  |  |  | August | August | SEALCOAT
|  |  | N Northaven Ln | NORTHAVEN | FOX POINT |  |  |  | October | October | CRF
|  |  | N Northcrest Dr | NEBRASKA | EOP NORTH |  |  |  | October | October | CRF
|  |  | N Old Trail Rd | WINTERBERRY | FORREST HILL |  |  |  | August | August | SEALCOAT
|  |  | N Park Edge Ct | FOX POINT | CUL-DE-SAC |  |  |  | August | August | SEALCOAT
|  |  | N Pinehurst Ct | EVERGREEN | CRESTWOOD |  |  |  | October | October | CRF
|  |  | N Renwood Dr | CINDY | RENWOOD |  |  |  | August | August | SLURRY SEAL
|  |  | N Riviera Ct | RIVIERA | CUL-DE-SAC |  |  |  | October | October | CRF
|  |  | N Ruff Ln | WILSHIRE | CUL-DE-SAC |  |  |  | August | August | SEALCOAT
|  |  | N Saddlehorn Ct | WILHELM | CUL-DE-SAC |  |  |  | August | August | SLURRY SEAL
|  |  | N Sandia Dr | W Palmyra Ct | W Reservoir Blvd |  |  |  | August | August | SEALCOAT
|  |  | N Stonewood Ct | FROSTWOOD | CUL-DE-SAC |  |  |  | August | August | SLURRY SEAL
|  |  | N Sunnyview Ct | SUNNVIEW | CUL-DE-SAC |  |  |  | October | October | CRF
|  |  | NE Glendale Ave | MARY | CUL-DE-SAC |  |  |  | October | October | CRF
|  |  | Pecan St | ADAMS | JEFFERSON |  |  |  | October | October | CRF
|  |  | W Arrowhead St | ARDELL | NORTHCREST |  |  |  | October | October | CRF
|  |  | W Augustana Ave | S Idaho St | S Folkers Ave |  |  |  | August | August | SEALCOAT
|  |  | W Broadmoor St | N St Marys Rd | N Lexington Dr |  |  |  | August | August | SEALCOAT
|  |  | W Chadwick Ln | FORSYTHE | ROCKVALE |  |  |  | August | August | SLURRY SEAL
|  |  | W Compton Ct | DEVONSHIRE | CUL-DE-SAC |  |  |  | August | August | SEALCOAT
|  |  | W Golf Creek Dr | RADNOR | CUL-DE-SAC |  |  |  | August | August | SLURRY SEAL
|  |  | W Hollow Trace Dr | SYLER | IDLEWHILE |  |  |  | August | August | SEALCOAT
|  |  | W Iron Cross Dr | HARVEST | OSAGE |  |  |  | August | August | SLURRY SEAL
|  |  | W Joan Ct | SHERIDAN | CUL-DE-SAC |  |  |  | August | August | SLURRY SEAL
|  |  | W Johnson Ct | W Merriman St | cul-de-sac to west |  |  |  | August | August | SEALCOAT
|  |  | W Lindy Ln | ASPEN | HUNTERS |  |  |  | October | October | CRF
|  |  | W Michele Ln | MICHELE | KIMBERLY |  |  |  | October | October | CRF
|  |  | W Millbrook Ct | Brookside | end to east |  |  |  | August | August | SEALCOAT
|  |  | W Nevada St | S Idaho St | SW Adams St |  |  |  | August | August | SEALCOAT
|  |  | W Newcastle Dr | EOP WEST | CUL-DE-SAC |  |  |  | August | August | SLURRY SEAL
|  |  | W Northpoint Dr | HUNTERS | CUL-DE-SAC |  |  |  | October | October | CRF
|  |  | W Ravine Ave | N Stever Ave | EOP East |  |  |  | August | August | SEALCOAT
|  |  | W Tara Cir | circle to the west | N Frostwood Pkwy |  |  |  | August | August | SEALCOAT
|  |  | W Vail Ct | HUNTERS | CUL-DE-SAC |  |  |  | October | October | CRF
|  |  | W Virginia Ave | W Loucks Ave | N North St |  |  |  | August | August | SEALCOAT
|  |  | W Wilshire Dr | ROCKVALE | CAPITOL |  |  |  | August | August | SEALCOAT
|  |  | W Wood Trail Ct | TRAIL VIEW | CUL-DE-SAC |  |  |  | August | August | SLURRY SEAL
|  |  | W Yorkshire Ave | RANDWICK | DEVONSHIRE |  |  |  | August | August | SEALCOAT
|  |  | W Whitehall Ct | FOX POINT | CUL-DE-SAC |  |  |  | October | October | CRF
|  |  | NE Monroe St | VAN BUREN ST | SPITZNAGLE AVE |  |  |  | August | August | SEALCOAT
|  |  | N North St | MCCLURE | MAIN | [5 empty] | SLURRY SEAL
|  |  | N Sheridan Rd | RUSSELL | WINDOM | [5 empty] | SLURRY SEAL
|  |  | MacArthur Hwy | Jefferson | Millman | [5 empty] | SLURRY SEAL
Ramp Construction
|  |  | W BUTLER ST | S SHELLEY ST | SW |  |  | SCHEDULED WORK
|  |  | W BUTLER ST | S SHELLEY ST | SE |  |  | SCHEDULED WORK
|  |  | W BUTLER ST | S SHELLEY ST | NE |  |  | SCHEDULED WORK
|  |  | W BUTLER ST | S SHELLEY ST | NW |  |  | SCHEDULED WORK
|  |  | W KETTELLE ST | S SHELLEY ST | SW |  |  | SCHEDULED WORK
|  |  | W KETTELLE ST | S SHELLEY ST | SE |  |  | SCHEDULED WORK
|  |  | W KETTELLE ST | S SHELLEY ST | NE |  |  | SCHEDULED WORK
|  |  | NE JEFFERSON ST | MORGAN ST | NW |  |  | SCHEDULED WORK
|  |  | W AUSTIN DR | N SHERIDAN RD | NW |  |  | ADDITIONAL WORK
|  |  | W AUSTIN DR | N SHERIDAN RD | NE |  |  | ADDITIONAL WORK
|  |  | W MARTIN ST | S WARREN ST | NE |  |  | SCHEDULED WORK
|  |  | W MARTIN ST | S WARREN ST | SE |  |  | SCHEDULED WORK
|  |  | W MARTIN ST | S WARREN ST | NW |  |  | SCHEDULED WORK
|  |  | W MARTIN ST | S WARREN ST | SW |  |  | SCHEDULED WORK
|  |  | N RICHARD PRYOR PL | W JOHN GWYNN JR AVE | NE |  |  | SCHEDULED WORK
|  |  | N RICHARD PRYOR PL | W JOHN GWYNN JR AVE | SE |  |  | SCHEDULED WORK
|  |  | N RICHARD PRYOR PL | W JOHN GWYNN JR AVE | NW |  |  | SCHEDULED WORK
|  |  | N RICHARD PRYOR PL | W JOHN GWYNN JR AVE | SW |  |  | SCHEDULED WORK
|  |  | E RAVINE AVE | N NEW YORK AVE | NE |  |  | SCHEDULED WORK
|  |  | E RAVINE AVE | N NEW YORK AVE | NW |  |  | SCHEDULED WORK
|  |  | E RAVINE AVE | N NEW YORK AVE | SE |  |  | SCHEDULED WORK
|  |  | E RAVINE AVE | N NEW YORK AVE | SW |  |  | SCHEDULED WORK
|  |  | W ALBANY AVE | N SHERIDAN RD | NW |  |  | SCHEDULED WORK
|  |  | W ALBANY AVE | N SHERIDAN RD | SW |  |  | SCHEDULED WORK
|  |  | W ALBANY AVE | N SHERIDAN RD | SE |  |  | SCHEDULED WORK
|  |  | W ALBANY AVE | N SHERIDAN RD | NE |  |  | SCHEDULED WORK
|  |  | E RAVINE AVE | N CALIFORNIA AVE | NE |  |  | SCHEDULED WORK
|  |  | E RAVINE AVE | N CALIFORNIA AVE | NW |  |  | SCHEDULED WORK
|  |  | E RAVINE AVE | N CALIFORNIA AVE | SE |  |  | SCHEDULED WORK
|  |  | E RAVINE AVE | N CALIFORNIA AVE | SW |  |  | SCHEDULED WORK
|  |  | SW MONROE ST | FULTON ST | NW |  |  | ADDITIONAL WORK
Residential Reconstruction
|  |  | Harvard Ave | Bishop Ave | Lake |  |  | 2016
|  |  | Columbine Dr | Hickory Grove Rd | Northtrail Dr |  |  | 2016 | July | September
|  |  | Stenning Dr | Ambriar Dr | Weaver Ridge Blvd |  |  | 2016 | August | October
|  |  | Delmar Ct | Cul -de-sac | Hudson St |  |  | 2016 | September | November
|  |  | Dennis Ct | Golf Dr | Village Dr |  |  | 2017 | April | July
|  |  | Dries Ln | Gilbert Ave | Wilcox Ave |  |  | 2017 | April | July
|  |  | Manor Pkwy | Moss Ave | Sterling Ave |  |  | 2016 | July | October
|  |  | Harvard Ave | Purdue St | Bishop Ave |  |  | 2017 | May | November
|  |  | Bodell Dr | Cul-de-sac | Collet Dr |  |  | 2018
|  |  | Circle Dt | Cul-de-sac | Glen Ave |  |  | 2018
|  |  | Harvard Ave | War Memorial Dr | Purdue St |  |  | 2018
|  |  | Brevis St | Harvard St | Homestead Ave |  |  | 2018
|  |  | Wilson Ave | Peoria Christian | Wisconsin Ave |  |  | 2018
|  |  | Kneer Ave | Freemont St | Arlington Ave |  |  | 2018
|  |  | Kneer Ave | Krause Ave | Arlington Ave |  |  | 2019
|  |  | Donald St | Valley Ave | Machin Ave |  |  | 2019
|  |  | Scenic Dr | Cul-de-sac | Lake Ave |  |  | 2019
|  |  | Geneva Rd | Forestglen Dr | Alta Rd |  |  | 2019
|  |  | Ligonier St | Antoinette St | Hayes St |  |  | 2020
|  |  | Winifred St | Hamilton Rd | Cherill St |  |  | 2020
|  |  | Bourland Ave | Cul-de-sac | Donald St |  |  | 2020
Sidewalk Construction
|  |  | Arlington Ave | Idaho | Laramie
|  |  | Starr St | Idaho | Laramie
|  |  | Folkers Ave | Hayes | Arlington
|  |  | Idaho | Arlington | Grinnell
|  |  | Folkers | Hayes | Alley |  |  | Additional Work
|  |  | Fremont | Idaho | Folkers |  |  | Additional Work
|  |  | Idaho | Arlington | Fremont |  |  | Additional Work